## Defects
SNO | Submitted Date | Description | Detected Sprint | Assigned to | Type of Defect | Severity | Action Taken | Action Taken Date | Status | Remarks
1 | 2025-11-27 | CSV preprocessing failure due to unicode encoding issue | Sprint 1 | Data Preprocessing Team | Functional | Medium | Changed encoding to latin1 and reloaded CSV | 2025-11-28 | Closed | Working as expected
2 | 2025-11-29 | Email body not cleaned properly (URLs not removed) | Sprint 1 | NLP Team | Functional | Low | Added regex cleanup rules for URLs | 2025-11-30 | Closed | Resolved
3 | 2025-12-01 | Label imbalance issues during dataset preparation | Sprint 1 | Data Preprocessing Team | Data | Medium | Applied resampling to balance dataset | 2025-12-02 | Closed | Balanced dataset
4 | 2025-12-07 | Logistic Regression underfitting during training | Sprint 2 | ML Team | Functional | Medium | Tuned hyperparameters and TF-IDF | 2025-12-09 | Closed | Improved accuracy
5 | 2025-12-10 | TF-IDF vectorizer mismatch between train & predict | Sprint 2 | ML Team | Technical | High | Saved and reused the same TF-IDF vectorizer | 2025-12-12 | Closed | Consistency achieved
6 | 2025-12-18 | Urgency detection misclassifying high cases as medium | Sprint 3 | ML Team | Functional | High | Added rule-based override for urgent keywords | 2025-12-20 | Closed | Improved recall
7 | 2025-12-22 | Streamlit fails to render charts on dashboard load | Sprint 3 | Frontend Team | Functional | Medium | Updated matplotlib rendering logic | 2025-12-23 | Closed | Charts visible
8 | 2025-12-26 | Filters not updating category and urgency charts | Sprint 3 | Frontend Team | UI | Medium | Refactored filter event logic | 2025-12-28 | Closed | Filter works as expected
9 | 2026-01-05 | Missing model files caused failure in deployment | Sprint 4 | DevOps Team | Technical | High | Uploaded model .pkl files to repo | 2026-01-07 | Closed | Deployment fixed
10 | 2026-01-12 | Deployment failing due to missing Python libraries | Sprint 4 | DevOps Team | Technical | High | Added missing packages to requirements.txt | 2026-01-14 | Closed | Environment stable
11 | 2026-01-18 | Predicted pie chart showing full solid color (poor UX) | Sprint 4 | Frontend Team | UI | Low | Removed predicted pie chart and cleaned UI | 2026-01-21 | Closed | UI improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others