## Product Backlog
| Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect real-world email datasets so that the system can be trained on realistic enterprise email data | MUST HAVE | Dataset availability | Data Engineer | 3- Completed
Sprint 1 | Sprint 1 | US002 | As an ML engineer, I want to clean raw email text so that noise does not affect model performance | MUST HAVE | Data Collection | Data Engineer | 3- Completed
Sprint 1 | Sprint 1 | US003 | As a data scientist, I want to preprocess cleaned emails for ML readiness | MUST HAVE | Data Preparation & Cleaning | Data Engineer | 3- Completed
Sprint 1 | Sprint 1 | US004 | As an ML engineer, I want to encode labels so models can learn effectively | MUST HAVE | Data Preprocessing | ML Engineer | 3- Completed
Sprint 1 | Sprint 1 | US005 | As an ML engineer, I want to convert text to numerical features | MUST HAVE | Data Preprocessing | ML Engineer | 3- Completed
Sprint 1 | Sprint 1 | US006 | As a data scientist, I want to split data to evaluate model performance | MUST HAVE | Label Encoding, Vectorization | Data Scientist | 3- Completed
Sprint 2 | Sprint 2 | US007 | As an ML engineer, I want a baseline classifier for email categories | MUST HAVE | Train/Test Split | ML Engineer | 3- Completed
Sprint 2 | Sprint 2 | US008 | As an ML engineer, I want a lightweight baseline classifier | MUST HAVE | Train/Test Split | ML Engineer | 3- Completed
Sprint 2 | Sprint 2 | US009 | As an AI engineer, I want to improve accuracy using transformers | SHOULD HAVE | Preprocessed Data | AI Engineer | 3- Completed
Sprint 2 | Sprint 2 | US010 | As an AI engineer, I want efficient transformer-based classification | SHOULD HAVE | Preprocessed Data | AI Engineer | 3- Completed
Sprint 2 | Sprint 2 | US011 | As a data scientist, I want to compare all models to select the best | MUST HAVE | All Models | Data Scientist | 3- Completed
Sprint 3 | Sprint 3 | US012 | As a support manager, I want urgent emails detected immediately | MUST HAVE | Preprocessing | ML Engineer | 3- Completed
Sprint 3 | Sprint 3 | US013 | As an ML engineer, I want urgency detected using ML | MUST HAVE | Train/Test Split | ML Engineer | 3- Completed
Sprint 3 | Sprint 3 | US014 | As a system designer, I want rule-based urgency to override ML when critical | SHOULD HAVE | Rule-Based + ML Urgency | AI Engineer | 3- Completed
Sprint 3 | Sprint 3 | US015 | As an ML engineer, I want to integrate and validate urgency prediction results so that the system reliably identifies critical emails. | MUST HAVE | Urgency prediction model | ML Engineer | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 94 | 4 | 6 | 7 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T-1 | Data Collection | 2025-11-27 | 2025-11-30 | Data Engineer | Data Gathering | 3- Completed | 8 | bar: Day 1 to Day 3
US002 | T-2 | Data Preparation and Cleaning | 2025-12-01 | 2025-12-05 | Data Engineer | Preprocessing | 3- Completed | 10 | bar: Day 2 to Day 5
US003 | T-3 | Data Preprocessing | 2025-12-06 | 2025-12-11 | Data Engineer | Feature Prep | 3- Completed | 8 | bar: Day 3 to Day 6
US004 | T-4 | Category Classification (Logistic Regression) | 2025-12-12 | 2025-12-15 | ML Engineer | Model Training | 3- Completed | 12 | bar: Day 1 to Day 3
US005 | T-5 | Category Classification (Naive Bayes) | 2025-12-16 | 2025-12-19 | ML Engineer | Model Training | 3- Completed | 10 | bar: Day 2 to Day 4
US006 | T-6 | Category Classification (DistilBERT) | 2025-12-20 | 2025-12-25 | AI Engineer | Transformer Training | 3- Completed | 24 | bar: Day 3 to Day 10
US007 | T-7 | Rule-Based Urgency Detection | 2025-12-26 | 2025-12-28 | ML Engineer | Urgency Rules | 3- Completed | 6 | bar: Day 1 to Day 2
US008 | T-8 | ML-Based Urgency Prediction | 2025-12-29 | 2026-01-04 | ML Engineer | Urgency ML | 3- Completed | 10 | bar: Day 2 to Day 4
US009 | T-9 | Hybrid Urgency Decision Logic | 2026-01-05 | 2026-01-08 | AI Engineer | Hybrid Logic | 3- Completed | 6 | bar: Day 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Raw emails contained HTML and noise | Applied HTML and regex-based cleaning
Sprint 1 | Day 2 | Missing values in email dataset | Removed null records and validated data
Sprint 1 | Day 3 | Large dataset slowing preprocessing | Optimized preprocessing pipeline
Sprint 1 | Day 4 | Label inconsistencies | Standardized category labels
Sprint 1 | Day 5 | Imbalanced data distribution | Reviewed dataset composition
Sprint 2 | Day 1 | Baseline model accuracy was low | Tuned TF-IDF parameters
Sprint 2 | Day 2 | Naive Bayes overfitting | Adjusted feature size
Sprint 2 | Day 3 | Transformer training very slow | Reduced batch size
Sprint 2 | Day 4 | High memory usage during training | Used DistilBERT instead of BERT
Sprint 2 | Day 5 | Evaluation metrics inconsistent | Used macro F1 for comparison
Sprint 3 | Day 1 | ML urgency missed critical emails | Introduced rule-based urgency
Sprint 3 | Day 2 | False positives in urgency detection | Refined urgency keywords
Sprint 3 | Day 3 | Conflict between ML and rules | Implemented hybrid override logic
Sprint 3 | Day 4 | Testing hybrid logic | Validated with sample emails
Sprint 3 | Day 5 | Final validation pending | Completed end-to-end testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-27 | 2025-12-11 | Data Engineer | Automate cleaning scripts | Manual cleaning steps | Using regex-based preprocessing | Standardized preprocessing pipeline
2 | Sprint 2 | 2025-12-12 | 2025-12-25 | ML Engineer | Hyperparameter tuning | Training without evaluation | Baseline + transformer comparison | Selected best-performing models
3 | Sprint 3 | 2025-12-26 | 2026-01-08 | AI Engineer | Hybrid urgency logic | Pure ML urgency detection | Rule-based overrides | Improved urgency precision
4
5
6
7